## Backlog
Quake3-iOS — Pending Work Backlog
Source: CLAUDE.md (project instructions). Generated 2026-04-19. Native cgame live (commit 5977485); four-pass render order opaque/filter/alpha/additive.
ID | Priority | Area | Title | Description / Next step | Status | Owner | Notes
B-01 | P1 | Shader / tcGen | Retest goat-skull wall relief scrolling | tcGen environment is implemented. Revisit staircase-adjacent goat-skull wall; confirm artifact gone. If not, verify metalShaderMap_t.tcGenEnv captured and ShaderMap_GetTcGenEnv returns true for the surface. | Verify
B-02 | P1 | Shader / tcMod | tcMod turb — switch proxy from texCoord to worldPos | worldPos is now piped through WorldVertexOut (655df55). If turb visually drifts, change ApplyTcMod tcMod==5 to use in.worldPos * (1.0/1024.0) instead of uv * 0.5. | Not started |  | Only touch if drift is visible
B-03 | P2 | Shader | rgbGen wave — pulsing flame brightness | Implement rgbGen wave in world/entity fragment path so flame/plasma surfaces pulse correctly. | Not started
B-04 | P2 | Shader | deformVertexes wave — flame/water surface wobble | Add deformVertexes wave support for flame/water geometry; likely vertex-shader side. | Not started
B-05 | P2 | Scene polys | Scene poly visual polish | RE_AddPolyToScene is implemented & routed through entity pipelines. Remaining: confirm smoke/blood/rail decal textures resolve to alpha blend for all cgame poly shaders. | In progress |  | Audit via AuditOnce logs
B-06 | P3 | Shader / tcMod | tcMod rotate — MSL implementation | Type is parsed by ParseShaderText but not yet rendered in ApplyTcMod. Add the rotate branch in the MSL world fragment tcMod switch. | Not started
B-07 | P4 | Portals / RTT | Portal RTT Phase-1 verification on q3dm1 | Phase-1 is LIVE (655df55). Verify RT_PORTALSURFACE entities actually reach RE_AddRefEntityToScene on q3dm1 teleporter via s_hasVisiblePortalEntity log. If native cgame doesn't submit it, use Q3MetalRenderer_GetPortalSmokeTest() to validate RTT pipeline independently. | Verify
B-08 | P4 | Housekeeping | Remove stale metal_debug_passes one-shot Cvar_Set | Default is now "0". The one-shot Cvar_Set("metal_debug_passes", "0") in stub overwrites the stale "2" in q3config.cfg. Safe to delete after one launch on each dev device. | Not started |  | Trivial cleanup
B-09 | P4 | Housekeeping | Remove AddWorldDrawStage AuditOnce STAGE logging | Intentionally left in place for future diagnostics. Remove once classification is confirmed stable across the full map set. | Not started
B-10 | P4 | Fallback cvars | Decide fate of metal_synth_viewmodel / metal_hide_nearby / metal_fallback_camera | All default 0 since native cgame (5977485). Retained as regression fallback. Decide whether to remove after further device soak. | Not started |  | Keep until broad map coverage

## Summary
Backlog Summary
Priority | Count | Notes
P1 | 2 | Next up — ship-blockers or highest-value fixes
P2 | 3 | Queued — visual polish / shader features
P3 | 1 | Nice to have
P4 | 4 | Verify / housekeeping
Total | 10
Status | Count
Not started | 7
In progress | 1
Blocked | 0
Verify | 2
Done | 0